## Sheet1
|  |  | User Story | [5 empty] | Status
Task Id | Name | As a… | I want to be able to… | So that… | Priority | Size | Sprint | To Do | Doing | Done | Added by | Comment
1 | Login | Administrator | login to the system | I can create users and assign roles. | 1 | 10 | 1 | X |  |  | PO
2 | Login | Administrator | login to the system | I can update informaton about a system user. | 3 | 3 | 1 | X |  |  | PO
3 | Login | Administrator | login to the system | deactivate users who should no longer access the system | 4 | 2 | 1 | X |  |  | PO
4 | Login | Administrator | login to the system | activate user to allow them to use the system. | 2 | 2 | 1 | X |  |  | PO
5 | Login | Administrator | reset passwords | users will be able to access the system | 5 | 2 | 1 | X |  |  | PO
6 | Create Chart of Accounts | Administrator | create entry for chart of accounts | users will be able to record journal entries | 6 | 10 | 2 | X |  |  | PO
7 | Update entry in Chart of Accounts | Administrator | update entry in the chart of accounts | I will ensure the database information is accurate. | 7 | 3 | 2 | X |  |  | PO
8 | Deactivate entry in Chart of Accounts | Administrator | deactivate a chart of accounts entry | the account will no longer be used in a transaction. | 8 | 1 | 2 | X |  |  | PO
9 | Search accounts | Administrator | search an account by name or account number | I will be able to view account details. | 11 | 3 | 2 | X |  |  | PO
10 | View accounts | Administrator | view an account detail | I will be able to make changes to the details. | 10 | 2 | 2 | X |  |  | PO
11 | View event reports | Administrator | view event logs | I will be able to review user activity. | 12 | 4 | 2 | X |  |  | PO
12 | Database setup | Administrator | setup the database | account related information can be stored in it. | 9 | 10 | 2 | X |  |  | PO
13 | View tables | Administrator | view each table in the databse | I can research the contents to respond to inquiries. | 13 | 2 | 2 | X |  |  | PO
14 | Edit tables | Administrator | edit table entries | I can correct errors found in account details. | 14 | 5 | 2 | X |  |  | PO
15 | View user reports | Administrator | view user statistics | I will understand the kinds of users we have in the system. | 15 | 2 | 2 | X |  |  | PO
16 | View login statistics | Administrator | get information about system use | I will make appropriate changes if there are issues. | 16 | 4 | 2 | X |  |  | PO
17 | View journal entries by status - pending, approved, rejected | Manager | View journal entries created by date | I will review the information and decide whether to approve it, reject it with a comment, or reset it so that the accountant can make changes to it. | 1 |  |  | X |  |  | PO
18 | Download attached document | Manager | download attached document to a journal entry | I will be able to print it or save it. |  |  |  | X |  |  | PO
19 | Post journal entry | Manager | approve a journal entry | it will post into the ledger. | 2 |  |  | X |  |  | PO
20 | Reject journal entry | Manager | reject journal entry submitted by accountant | the account will not post into the ledger. | 3 |  |  | X |  |  | PO
21 | Request new account to be added | Manager | request new account to be added to the chart of accounts | accounts will have the account they need to capture a journal. | 5 |  |  | X |  |  | PO
22 | Request existing account edit. | Manager | request the administrator to edit existing account found in the chart of accounts | an erroneous entry can be corrected. | 4 |  |  | X |  |  | PO
23 | View income statement | Manager | view the income statement | I will be able to assess financial activity during a period. | 9 |  |  | X |  |  | PO
24 | View balance sheet | Manager | view the balance on each of the accounts | I can assess the balance of each account. | 10 |  |  | X |  |  | PO
25 | View staetment of retained earnings | Manager | review the retained earnings balance | I can decide the retained earnings position at the beginning and end of the period. | 11 |  |  | X |  |  | PO
26 | View accounts | Manager | view an account detail | I will be able to assess the information and determine if changes are necessary. | 6 |  |  | X |  |  | PO
27 | View trial balance | Manager | view the trial balance | I will be able to review the account balances. | 7 |  |  | X |  |  | PO
28 | View ledger | Manager | view account ledger | I will be able to view individual account activity and understand the balance of each account. | 8 |  |  | X |  |  | PO
29 | Create journal entry | Accountant | jounralize transactions | I will be able to capture financial activity in the books. | 1 |  |  | X |  |  | PO
30 | Submit journal entry | Accountant | submit a journal entry recorded | it will be reviewed by a manager for approval. | 2 |  |  | X |  |  | PO
31 | View status of submitted journal entries | Accountant | view the approval status of each of the jounal entries submitted | I will know where all the journal entries are approved and posted. | 3 |  |  | X |  |  | PO
32 | Create trial balance | Accountant | create a trial balance by date | I will be able to view account balances as of a specific date. | 4 |  |  | X |  |  | PO
33 | Create income statement | Accountant | generate income statement by date | I will review the current financial operaton. | 5 |  |  | X |  |  | PO
34 | Create balance sheet | Accountant | generate a balance sheet by date | I will determine the balance of each account in the system. | 6 |  |  | X |  |  | PO
35 | Create retained earnings staetment | Accountant | generate a retained earnings statement by date | I will review the retained earnings position at the beginning and end of the period. | 7 |  |  | X |  |  | PO
36 | Create ratio analysis | Accountant | generate financial ratios | I will be able to assess the financial health of the company. | 8 |  |  | X |  |  | PO
37 | View event log reports | Accountant | view the event log report | I will be able to review the change history in the system | 9 |  |  | X |  |  | PO
38 | Create dashboards | Accountant | view the financial dashbords | to review the financial status of the sytem visually. | 10 |  |  | X |  |  | PO
39 | Download a report - income statement, balance sheet, trial balance, ratio analysis, event log, dashboard | Accountant | download the financial reports | I can save, print or share it with interested parties. | 11 |  |  | X |  |  | PO
40 | Download attachment | Accountant | download attached document to a journal entry | I can save, print or share it with interested parties. | 11 |  |  | X |  |  | PO
41 | Request new account to be added | Accountant | request new account to be added to the chart of accounts | accounts will have the account they need to capture a journal. | 12 |  |  | X |  |  | PO
42 | Request existing account edit. | Accountant | request the administrator to edit existing account found in the chart of accounts | an erroneous entry can be corrected. | 13 |  |  | X |  |  | PO
43 | Create SRS | [6 empty] | X |  |  | PO
44 | Create SDS | [6 empty] | X |  |  | PO
45 | Create STS | [6 empty] | X |  |  | PO
46 | Create User Manual | [6 empty] | X |  |  | PO
47 | Create demo video of finalized application and upload to Youtube | [6 empty] | X |  |  | PO
48 | Create Flyer for your Software | [6 empty] | X |  |  | PO
49 | Create Logo for your Software | [6 empty] | X |  |  | PO
50 | Create Use Cases for the behavior of the software | [6 empty] | X |  |  | PO
51 | Create Class Diagrams | [6 empty] | X |  |  | PO
52 | Create User Interface for each of the screens | [6 empty] | X |  |  | PO
53 | Create a database diagram | [6 empty] | X |  |  | PO
54 | Create Report Template for each of the Reports in the System | [6 empty] | X |  |  | PO
55 | Create a template for the journalizing page. | [6 empty] | X |  |  | PO
56 | Create a template for the manager view page. | [6 empty] | X |  |  | PO